## List
[10 empty] | Applicable Goals & Objectives (Value to Coho - L=Low/M=Medium/H=High/E=Essential) | [12 empty] | Action Types (Status(C=Completed, A=Active, Pe=Pending, Pr=Proposed)/Feasibility (L/M/H)/Life Stage Addressed (AM=Adult Migration, SI=Spawning/Incubation, FD=Fry Dispersal, SRd=Summer Redistribution, SRe=Summer Rearing, FR=Fall Redistribution, WR=Winter Rearing, SO=Smolt Outmigration)
[10 empty] | I | I | II | VI | VI |  | VI | VII |  |  |  |  | VII | Culvert or road crossing improvement | Manual fish passage improvement | Instream barrier removal/modification | Gravel augmentation | Instream structure augmentation or placement | Cover placement | Riparian protection, planting and fencing | Floodplain restoration | Habitat restoration (off-channel/side channel) | Diversion screening/modification | Monitor/measure water diversions | Water leasing/flow augmentation/transfers | Reduce/reclaim/treat tailwater | Improve water conservation and conveyance | Identify and treat point source pollution | Conduct feasibility studies to increase potential for restoration projects | Land acquisition/conservation easements | Encourage beaver recolonization | Education/outreach to stakeholders |  |  |  | Extent of Refugial areas, known
[10 empty] | A1 | A2 | C1 | G1 | G2 |  | I1 | J2 |  |  |  |  | K2
Locations | Coho Pop. Area | River Mile (RM) | River Kilo (RK) | Watershed Area (Acres) | Coho Habitat Spawning (miles) (Cramer) | Coho Habitat Rearing (miles) | Coho Habitat (miles) (MKWC/USFS/Karuk) | High Quality Coho Habitat (miles) | Limiting Factors, (anthropogenic, in order of importance) | Improve access | Remove/modify permanent barriers | Improve sediment recruitment and function | Enhance cover at refugia | Increase extent of summer refugia | Increase extent of winter rearing habitat | Restore channel structure and complexity | Improve instream flows | Reconnect channel to the floodplain | Improve water quality | Increase spawning habitat | Prevent entrainment | Protect summer rearing habitat | [19 empty] | Current Projects | Proposed Projects | Specific Projects to Be Accomplished |  | Notes/Comments - Other Species Concerns | Projects Completed
Upper Klamath
Klamath Mainstem IGD to Spencer Creek | UK | [9 empty] | E
Upper Klamath mainstem (IGD-Shasta) | UK | [5 empty] | 62 |  | Dynamic flow regime, water quality, water quantity, disease, channel/floodplain function |  | H | M | H | H | M | H | H | H | H | M | L | H |  |  |  | Pe/H/SI-SRe?-SO? |  |  | Pr/M/Sre | Pr/M/WR | Pr/M/SI-WR | ? | Pr/M/Sre |  |  |  | A/H/FD-Sre |  |  |  | A/M/All | Dam Removal slated to begin in 2021,Community Outreach and Education (UMKWC/NCRC - Current) | Gravel Augmentation (PacifiCorp - Pending) | Annually enhance gravel downstream of Iron Gate Dam according to gravel resource management plan. Exclude cattle from riparian areas and revegetate. |  | Lack of gravel above Cottonwood Creek affects chinook spawning and lamprey distribution, and increases polychaete populations.
Upper Klamath mainstem (Shasta-Scott) | [8 empty] | Dynamic flow regime, water quality (temperature), water quantity, fish disease, channel/floodplain function |  |  | M | H | H | H | H | H | H | H | M | L | H |  |  |  | Pr/H/SI-SRe?-SO? | Pr/H/SI,Sre,WR |  | Pr/M/Sre | Pr/H/WR | Pr/H/SI-WR | ? |  | Pr, M, Sre |  |  | A/H/AM, FD,Sre (Shasta) | A/H/All (Need More) | Pr/M/SI, SRe, WR |  | A/M/All | Community Outreach and Education (UMKWC/NCRC /MKWC- Current), Mainstem above Humbug Creek off-channel pond and side channel design project (Funded,2020 implementation date, USFS/MKWC/Karuk), Horse-Trough Springs(Seeking Design Funding, FRGP) |  | Assess benefits of gravel augmentation for this reach. Exclude cattle from riparian areas and revegetate. Consider channel reconstruction where extensive mining occurred (Seiad Valley to Shasta River). Re-connect side channels interrupted by past mining/current gravel mining operations. Increase flows from tribs into Klamath mainstem. |  | Ongoing disease studies may inform future restoration (gravel augmentation) actions in this reach. Dam removal is likely single most important restoration action for this reach.
Upper Klamath mainstem (Scott-Indian) | [8 empty] | Water quality (temperature), water quantity, fish disease, channel/floodplain function |  |  | L | H | H |  | L | H | M | H |  |  | H | [6 empty] | Pr/M/Sre | Pr/H/WR | Pr/H/SI-WR |  |  | Pr, M, Sre (Cade) |  |  | A/H/AM, FD,Sre (Scott) | A/H/All (Need More) | Pr/M/SI, SRe, WR |  | A/M/All | Community Outreach and Education (UMKWC/NCRC /MKWC- Current), Klamath Tributary Fish Passage Improvement (MKWC/Karuk/NFWF), Klamath Tributary Coho Habitat Enhancement | Ishkaysh Ranch Riparian Planting Project (Karuk - Proposed)(Moderate to low priority)(MKWC/Karuk/NFWF) | Consider channel reconstruction where extensive mining occurred (Seiad Valley to Shasta River). Re-connect side channels interrupted by past mining. Increase flows from tribs into Klamath mainstem. Riparian planting. |  | Summer base flow augmentation in the Scott River will benefit this reach. | Tom Martin Creek Coho Habitat Enhancement (MKWC/FWS), O'Neil Creek Coho Habitat Enhancement (Caltrans/USFS/MKWC/NCRWQCB ),
Bogus Creek | UK | 190.21 | 306.09 |  | 18.2 |  | 9.6 |  | Diversions/fish screens, fish passage, instream habitat, water quantity, water quality, IGD, hatchery practices | L | H |  | L | H | H | H | M | L | H | H | M | H |  |  | A?H/AM, SRd |  | Pr/H/SI, SRe, WR |  |  |  | Pr/M/WR | A/H/All | Pe/H/SRe |  | A/H/Sre | A/H/Sre |  | Pr/H/All |  |  | A/H/All | Klamath Tributary Fish Passage Improvement (MKWC/Karuk - Current), Coho Spawner Surveys (Monitoring, MKWC,PacifiCorps) | Talk to Mark Elfgen about potential outreach or needs for Bogus (MKWC,CDFW,USFWS) | Install 3 new water diversion structures replacing existing board dams. Work with private landowners to improve land management activities that promote floodplain health and resilience. Improve irrigation efficiencies. | extensive | Bogus Creek, due to it's proximity to the hatchery, is likely not a good place to collect wild salmon brood stock, Fish ladder is in poor condition (on Cold Creek and Bogus Mainstem) | Bogus Creek Water Diversion Structure Replacement Design and Engineering (Completed 2018)
Cold Creek (part of Bogus) | UK | [7 empty] | Diversions, Instream Habitat, Fish Passage, | H | H | L | L | H | H | M | M | L | M | M? | M | H |  | A/H/AM,SI,SRd | Pr/H/AM, SI, SRd, FRd |  | Pr/M/SI, SRe, WR |  |  |  | Pr/L/Sre,WR | Pr/H/FD,Sre,WR | Pr/L-M/All |  |  | A/H/All |  | Pr/H/All |  |  | A/H/All |  |  | Work with private landowners to improve land management activities that promote instream habitat complexity and fish passage. Conduct assessment of Cold Creek watershed to determine appropriate coho habitat restoration actions. Study life history/movement of coho in Cold Creek. |  | Cold Creek Fish Ladder is in poor condition for juvenile fish passage(needs evaluation) Likely no passage for juvies. Another barrier at upper reach of Cold Creek(Needs evaluation). DFG maintains ladder. Discussion whether or not to remove/ upgrade? DFG stocked Brown Trout in late 30's in upper reach. High priority to maintain water quality. | Cold Creek DFG Fish Screen Project (Completed 2018,DFG/Landowners)
Little Bogus Creek | UK | [7 empty] | Flow, Instream Habitat, Lack of Information | [34 empty] | Conduct basic assessment to determine nature of flows (duration/magnitude), fish use, and restoration potential. Landowner outreach needed | bar: L; M
Brush Creek | UK | [7 empty] | Lack of Information | [34 empty] | Conduct basic assessment to determine nature of flows (duration/magnitude), fish use, and restoration potential.Landowner outreach needed
Willow Creek | UK | 185.51 | 298.54 |  | 39.4 |  |  |  | Instream flows, Lack of Information, Fish Passage, Instream Habitat, Lack of Information, Channel Reconfiguration | [15 empty] | Pr/H/All |  | Pr/H/All | [15 empty] | Willow Creek Fish Passage and Habitat Improvement (NCRC) | Implement fish passage and habitat improvement along 2 miles of Willow Creek. Conduct basic assessment to determine nature of flows (duration/magnitude), fish use, and restoration potential. Landowner outreach needed (Morgan at CDFW is a good contact about Willow) | mouth to 200ft | Steelhead observed in 1980's. Low gradient makes potential for coho habitat, but flows are the limiting factor. | bar: H to H; H to M; L
Cottonwood Creek | UK | 182.51 | 293.7 |  | 44.4 |  | 4 |  | Instream flows/water quantity, water quality (temperature), barriers/diversions, sediment recruitment, riparian habitat, roads/altered hydrology | H | H | H | L | H | H | H | E | L | H | H | H | H | Pe/H/AM, FD, Sre, SRd | A/M/SRd, Sre | Pr/H/AM,SRd,Sre | Pr/H/SI | Pr/H/All |  | Pr/H/SI, Sre, SRd,WR | Pr/L/WR | Pr/M/WR | Pr/H/All | Pr/H/All | Pr/L/All | Pr/L/All | Pr/M/All | Pr/M/ All | Pr/H/All |  | Pr/M/All | A/H/All | Cottonwood Creek Cattle Crossing Upgrade (FWS/Forest Products/NCRC) | Hornbrook Municipal Water System Upgrade (Need Proponent/More Research), Cottonwood Creek Exclusion Fencing (NCRC), Water Diversion Upgrade, Cottonwood Creek Instream Habitat Structure (NCRC), Lower Cottonwood Creek Tailwater Irrigation System (NCRC), Lower Cottonwood Creek Fish Screen and Diversion Improvement (NCRC) | Improve summer base flow. Recruit gravel. Exclude cattle from riparian areas and revegetate. Install 3 miles of exclusion fencing along mainstem Cottonwood Creek.Re-introduce or encourage beavers. Work with private landowners to improve land management activities that promote floodplain health and resilience. Assess feasibility of water conservation/water transfers. Identify and treat point source pollution. Improve diversion structures. Repair and improve 5 livestock stream crossings on Cottonwood Creek. Install instream habitat structures over a linear length of 0.75 miles. Install tailwater irrigation system to improve water efficiency and quality. Improve existing diversion with fish screen and measuring device. Detailed Watershed Assesment is needed to determine limiting factors | extensive | Based upon its strategic position and low gradient, Cottonwood Creek has intrinsic restoration potential. However, without focused restoration efforts, it will not be a major fish producing stream. Landowner outreach is needed to gain access to more of the creek. | Cottonwood Creek Fish Barrier Removal (R Ranch/NCRC)(Completed 2016)
Dry Creek | UK | 188.7 | 303.68 | [5 empty] | Stranding | [15 empty] | Pr/M/SRd | [18 empty] | Modify lower 300'+ at mouth to allow fish passage out of Dry Creek into the Klamath River. |  | Lower 300' goes subsurface in June, stranding coho upstream. These fish are trapped and moved, or die, as the stream completely dries up by July. Important steelhead stream | bar: H to H
Williams Creek | UK | [7 empty] | Stranding | H: L/M; L: H; L: H; M: H; M: H? | Pr/H/FD, SRd |  |  |  | Pr/Sre, WR | Pr/Sre | [9 empty] | Pr/H/All | [5 empty] | Conduct basic assessment to determine existing conditions, nature of flows (duration/magnitude), fish use, and restoration potential. Assess box culvert on Klamathon Road (County) near highway. |  | Could be significant non-natal rearing or spawning in permanently wetted channel upstream.
Humbug Creek | UK | 171.81 | 276.48 |  | 11.2 |  | 7.4 |  | Adult and juvenile fish passage, culvert barriers?,altered channel hydrology | M? | M? |  | M | L | M? | H | ? | ? |  |  |  |  | ?/Need to assess | [6 empty] | Pr/L/FD, SRd, Sre, FR, WR | Pr/L/FD, SRd, Sre, FR, WR | [7 empty] | Pr/H/All |  | A/H/All |  | Humbug Creek Channel Reconfiguration (MKWC - Proposed) | Relocate roads out of riparian areas. Work with private landowners to improve land management activities that promote floodplain health and resilience. Add LWD to improve spawning gravel recruitment. Assess potential instream barriers. Assess potential for conservation easement at mouth. Removal of dikes above and below creek is high priority. Removing large tailing piles to re-open floodplain of creek. | variable depending on water yr | Work to restore upslope processes (fire regimes, road restoration) would help restore instream function. Purchase of these properties by a landtrust will be essential for restoration | Mid Klamath Coho Rearing Habitat Enhancement (MKWC/Karuk - Current)
Dutch Creek | UK | [7 empty] | Lack of Information | [36 empty] | DFG made initial contact with owner at the mouth to assess restoration potential. Follow up with DFG about landowner contact, investigate water conservation opportunities. Drive FS road along Dutch to assess. habitat potential. Fill out rest of CAT table when more information is collected.
Empire Creek | UMK | 166.55 | 268.02 | 6 | 6 | 6 |  |  | Excessive Sediment, Fish Passage | [13 empty] | Pr/H/All |  | Pr/H/All | [17 empty] | Empire Creek Road Crossing/Fish Passage Improvement (NCRC), Box culvert removal/replacement with bridge(CalTrans) | Treat 6 road stream crossing sites to reduce sediment and improve fish passage. |  | Complete snorkey survey to assess presence/absence of salmonids. More information is needed on current state of habitat. Fill out CAT when more habitat information is aquired | Mid Klamath Coho Rearing Habitat Enhancement (MKWC/Karuk - Current) | bar: H to L; M to M?
Lumgrey Creek | UK | 166.55 | 268.02 | [5 empty] | Lack of Information, Sediment? Fish passage? | [33 empty] | Box culvert needs replacement |  |  | NCRC working with landowners to identify projects. | Mid Klamath Coho Rearing Habitat Enhancement (MKWC/Karuk - Current)
Beaver Creek | UK | 161.67 | 260.16 |  | 25.3 |  | 23.2 |  | Sedimentation (Roads in Riparian), Reduced Summer Flows, Fish Passage, Floodplain connectivity,LWD/Instream structure, Lack of Beaver | L | M | M | H | H | H | H | H | H | M | M |  |  | Pr/H/All |  |  |  | Pr, M,WR-SRe | A, H, Sre | Pr, M, SI-Sre | Pr/M/ All | Pr, H, Sre-WR | Pe, H, All | Pe, H, All | Pe, H, All |  | Pe, H, All |  | Pe, M, Sre, WR |  | Pr, M, All | A/ M/ All | Klamath Tributary Fish Passage Improvement (MKWC/Karuk - Current); Beaver Creek off-channel pond planning and design (USFS/MKWC/KTFP) | West Fork Beaver Creek Road Crossing/Fish Passage Improvement (NCRC), construct 2-3 off-channel ponds on FS land above Highway 96 bridge. West Beaver wood loading project(Proposed) | Exclude cattle from riparian areas and revegetate. Relocate roads out of the floodplain. Place LWD. Re-introduce or encourage beavers. Work with private landowners to improve land management activities that promote floodplain health and resilience. Treat 4 road stream crossing sites to reduce sediment and improve fish passage. Create off-channel rearing sites at strategic locations. | extensive | Keep submitting West Fork Beaver wood loading proposals
Little Humbug Creek | UK | 158.47 | 255.03 |  | 0.6 |  | 0.1 |  | Instream flows, Lack of Information | [14 empty] | A, H, Sre | [17 empty] | Klamath Tributary Fish Passage Improvement (MKWC/Karuk - Current) |  |  | mouth to 1.0 mile | Significant source of gravel for the Barkhouse side channel just downstream. | bar: H to H
Barkhouse Creek | UK | [7 empty] | Instream Flows, Fish Passage, Lacking instream structure and function | [34 empty] | Investigate diversion and take flow measurements, could be a good candidate for BDA's to store and slow water(MKWC) |  | Re-introduce fire process to restore natural landscape process
Dogget Creek | UK | [7 empty] | Fish Passage, Water Quantity | H | H | M | L | H | H | H | H | H | M | M | H | TBD | H/AM | Pr/H/AM |  |  | Pr/AM,SI,Sre,WR | TBD | NA | Pr/L/AM,Sre,WR | Pr/L | Pr/H/All | Pr/H/All |  | Pr/H/All | Pr/H/All |  |  |  | Pr/H/All | Pr/H/All |  | Box culvert needs replacement | Culvert replacement , water conservation outreach to diversion landowners |  | Gather more information about physical and biological potential
McKinney Creek | UK | 155.28 | 249.89 |  | na |  | 1 |  | Fish Passage, Channel Structure/Lack of LWD | [13 empty] | Pe, H, AM, SRd, FR |  |  |  | PR, H, All |  | Pr, L, Sre |  | Pr, M, Sre,WR? | [10 empty] | Sisk. CO Dept. Pub. Works - Barrier Removal - Proposed |  | Improve channel function near mouth. Replace undersized culverts on county road near mouth with bottomless arch. Exclude cattle from riparian areas. | none | Seeking matching funds ($180,000) Planned to be completed within five years | bar: H; M; H
Horse Creek | UK | 148.15 | 238.41 |  | 16.9 |  | 8.7 |  | Channelization/Lack of Floodplain Connectivity, Fish Passage, Channel Structure/Lack of LWD, Instream Flows (Summer Base Flows), Lack of Beaver, Lack of low/no velocity rearing habitat | H: H; H: M? County X-ing Middle Creek; H: H; H: H; M: H; M: M; L: H | Pr,M, SRd | A, H, SRd | Pr,???, SRd |  | Pr, L, All |  | Pr, L, Sre | Pr, L, All | Pr, M, Sre,WR |  | Pr, M, Sre, SRd | ??? | ??? | ??? |  | Pr,M, All | Pr, ??, All | Pr, M, All | Pr, M, All | Klamath Tributary Fish Passage Improvement (MKWC/Karuk - Current), Mid Klamath Coho Rearing Habitat Enhancement (MKWC/Karuk - Current), Fish Gulch off-channel ponds and woodloading project (secured, summer 2018), Horse Creek Design/woodloading (MKWC/Karuk, secured), Middle Creek OCP Design/Implementation (MKWC/Karuk, secured), Middle Creek Design (MKWC, secured) | Implementation of off-channel/side channel/woodloading/channel reconfiguration on 1.5 miles of Horse Creek in lower valley (MKWC/Karuk). Implementation of channel rehab/riparian rehab on 3300' of lower Middle Creek (MKWC/Karuk). Upslope treatments of burned areas on private property within Horse Creek and Middle Creek valleys (MKWC). Heli woodloading in upper Horse Creek, above burned area (USFS). Post fire revegetation within burned riparian reserve (Caltrans/USFS). | Exclude cattle from riparian areas and revegetate. Place LWD. Re-introduce or encourage beavers. Re-align channel at mouth. Create off-channel habitats. Reconnect floodplain. | none at mouth, off channel pools yes | Follow up on culvert to groundwater pond - potential OCP project, Middle Creek culvert replacement (sisk CO) Check further. | DeCoursey off-channel pond constructed on Middle Creek (2014); Goodman off-channel pond constructeed on Middle Creek (2015); Upper and Lower Lawrence off-channel ponds constructed on Horse Creek (2017)
Tom Martin Creek | UK | 142.89 | 229.95 |  | na |  | 0.1 |  | Extent of refugia | [14 empty] | A, H, SRd |  |  |  | A, H, Sre, Srd | Pe/H/Sre |  | Pe/H/Sre,SRd | [10 empty] | Klamath Tributary Fish Passage Improvement (MKWC/Karuk - Current), Mid Klamath Coho Rearing Habitat Enhancement (MKWC/Karuk - Current), |  | Place LWD. Maintain fish passage to reach below Hwy 96 culvert. Place brush bundles in creek and at mouth. | extensive | These efforts are aimed to address the importance of Tom Martin as a thermal refuge for juvenile coho outmigrating from the Scott River. | Tom Martin Creek Off-Channel Habitat Project was constructed (2013, MKWC/Karuk) | bar: H; L to H
Negro Creek | UK | 138.2 | 222.39 |  | na |  | na |  | Fish Passage | [13 empty] | Pr/L/SRd | ? | [16 empty] | Pr, M, All |  | Negro Creek Culvert Removal | Remove culvert at mouth and replace with bridge or bottomless arch to allow non-natal fish passage to lower reach. |  | Decent potential non-natal coho rearing on lower reach. | bar: H to H
O'Neil Creek | UK | 137.63 | 221.49 |  | na |  | 0.1 |  | Fish Passage, Lack of Rearing Habitat | [14 empty] | A, H, SRd | [6 empty] | Pe, H, Sre, WR | [10 empty] | Mid Klamath Coho Rearing Habitat Enhancement (MKWC/Karuk - Current) |  | Improve fish passage at mouth by mechanically modifying boulder cascade. Add off channel habitat at mouth on Klamath floodplain and revegetate. Improve channel function and connectivity under Hwy 96 bridge. | ? |  | O'Neil Creek Pond Project (2013, Caltrans/USFS/MKWC/Karuk) | bar: H; L to H
Walker Creek | UK | 133.69 | 215.14 |  | 4 |  | 1.6 |  | Channel Complexity, Lack of LWD, Connectivity to Floodplain, Excessive Sediment, Entrainment/Unscreened Diversion, Fish Passage (Cobble Diversion Dam) | [14 empty] | A, H, SRd | Pr,???, SRd |  |  | A,H, Sre |  | Pr, ??, WR |  | Pr, M, Sre | Pr, H, Sre |  |  | Pr, H, Sre | [5 empty] | Klamath Tributary Fish Passage Improvement (MKWC/Karuk - Current), Mid Klamath Coho Rearing Habitat Enhancement (MKWC - Current) | Walker Creek Diversion Improvement (NCRC - proposed to NFWF/PC) | Concentrate channel flow and/or step pool construction to maintain juvenile and adult fish passage. | bar: H; L to H
Grider Creek | UK | 130.68 | 210.31 |  | 11.8 |  | 11.8 |  | Channelization/Lack of Floodplain Connectivity, Fish Passage, Channel Structure/Lack of LWD | [14 empty] | A, H, SRd | Pr, H, AM, FD, SRd, FR |  | Pr,H, AM, FD, SRd, FR |  | Pr, H, Sre, WR, SI | Pr, H, Sre, WR, SI | Pr, H, Sre, WR | [6 empty] | Pr, H, SI, Sre, WR, SRd, FR, FD, AM | Pr, H, AM, SI, FD, SRd, Sre, FR, WR | Pr, H, Sre, WR | A, H, All | Klamath Tributary Fish Passage Improvement (MKWC/Karuk - Current), Mid Klamath Coho Rearing Habitat Enhancement (MKWC/Karuk - Current) |  | Encourage beaver re-introduction. Add off channel ponds. Manual channel modification seasonally to promote fish passage. Work with private landowners to improve land management activities that promote floodplain health and resilience. Improve fish passage on new channel. Stop headcutting on new channel. | bar: H to H
West Grider Creek (part of Grider Creek) | UK | 130.68 | 210.31 |  | na |  | 0.5 |  | Fish Passage | [14 empty] | A, H, SRd, WR |  |  | Pr, H, AM, Sre, Sre, FR, WR |  |  |  | Pr, H, Sre, WR | [10 empty] | Klamath Tributary Fish Passage Improvement (MKWC/Karuk - Current), Mid Klamath Coho Rearing Habitat Enhancement (MKWC/Karuk - Current), Seiad/West Grider Coho Winter Rearing Habitat Restoration (MKWC/Karuk - Current) |  | Address instream barrier near confluence with Grider Creek through LWD structure placement. Add LWD to lower reach. | Spring fed, extensive |  | Grider/West Grider Off-Channel Rearing Habitat Project was constructed (2012, MKWC/Karuk) | bar: H; L to H
Canyon Creek (part of Seiad) | UK | 130.5 | 210 |  | na |  | 0.5 |  | Fish Passage | [13 empty] | Pr, H, AM,SRd, FR | [19 empty] | Replace Seiad Creek Road culvert barrier with bridge or bottomless arch. Very high priority. | Remove barrier at county road crossing. Replace culvert with bridge or bottomless arch. | bar: H to H
Seiad Creek | UK | 130.5 | 210 |  | 10.1 |  | 6.5 |  | Instream flows, floodplain connectivity, fish passage | H | H |  |  | M | H | H | H | H | L | H | H | H | Pr/M/SI,FD, Sre | A/H/SI,FD,SRd, Sre |  |  | Pe/H/SI, FD, SRd, Sre, WR |  |  | Pe/H/SI, FD, SRd, Sre, WR | A/H/Sre,WR | Pr/M/FD, SRd,FR | Pr/M/All | [8 empty] | Klamath Tributary Fish Passage Improvement (MKWC - Current), Mid Klamath Coho Rearing Habitat Enhancement (MKWC - Current), Seiad at Panther Gulch Design Project: off-channel ponds/side channel connectivity/woodloading (MKWC,USFS, current) | Seiad at Panther Gulch Implementation Project, Phase 1: off-channel pond construction (MKWC/USFS, pending) | Create off-channel winter rearing habitat near limit of anadromy and reconnect side channels by removing relic push up levees. | ? |  | Durazo Off-Channel Ponds constructed (2015), Seiad Creek Coho Habitat Enhancement Project implemented (2017)
Portuguese Creek | UK | 128.06 | 206.08 |  | na |  | 0.4 |  | Fish Passage, Lack of LWD | [13 empty] | Pr, H, AM,SRd, FR | A, H, AM, SRd |  |  | Pr, H, Sre, WR | [14 empty] | Klamath Tributary Fish Passage Improvement (MKWC/Karuk - Current), Mid Klamath Coho Rearing Habitat Enhancement (MKWC/Karuk - Current) |  | Place LWD in lower reach. Step pool construction around boulder cascade at mouth. Replace Hwy 96 culvert with a bridge. |  | Hwy 96 culvert replacement should occur before LWD placement in lower reach. Habitat assessment and fish passage assessment reports completed by Karuk Tribe. | bar: H to H
Barkhouse Creek | UK | [7 empty] | Fish Passage, Instream Flows, Gravel Aggradation at County Road Crossing | M |  | H |  |  |  | H | H | H | H | M | ? |  | Pr,?, AM, Sre, FR |  | Pr, ?, AM, Sre, FR |  |  |  | Pr, ?, Sre, SI, WR | Pr, ?, Sre, SI, WR | Pr, ?, WR | ? | ? | ? |  |  |  | Pr, ?, All | ? | Pr, ?, Sre, WR | Pr, H, All |  |  | Improve flow. Improve channel function. Install cattle exclusion fencing. Evaluate County road crossing, address gravel accumulation at crossing. Improve riparian vegetation.
Vesa Creek | UK | [7 empty] | Fish Passage | H: L?; H: ?; M: M; M: ? | [15 empty] | Pr, ?, All | [5 empty] | Remove Mine tailings at mouth. Improve channel connection to mainstem. Conduct further assessments to determine potential value of restoration actions to coho.
Middle Klamath
Middle Klamath mainstem (RM 43-127) | MK | [5 empty] | 84 |  | Riparian Restoration, Improve Summer Refugia, Reconnect Channel to Floodplain | [18 empty] | A, H, Sre | Pr,H, Sre | Pr, M, SI, Sre, WR | Pr, M, SI, Sre, WR | [6 empty] | Pr, H, All | Pr, ?, All | Pr, ?, All | A, H, All | Klamath Tributary Fish Passage Improvement (MKWC/Karuk - Current), Mid Klamath Coho Rearing Habitat Enhancement (MKWC/Karuk - Current) | Ishkaysh Ranch Riparian Planting Project (Karuk - Proposed) | Restore connectivity to floodplain in Happy Camp valley and other low gradient reaches. Riparian restoration. Mine tailing reclamation (above Happy Camp to China Creek). | bar: H to H
Fort Goff Creek | MK | 127.31 | 204.87 |  | 1.6 | 1.5 | 1.5 | 1.5 | Adult Fish Passage, Entrainment | [13 empty] | Pr, H, AM, SRd, FR | A, H, SRd, FR |  |  |  | A, H, Sre |  |  | Pr, ?, WR | Pr, ?, Sre | ? | ? |  | ? |  | Pr, H, All |  |  | Pr, H, All | Klamath Tributary Fish Passage Improvement (MKWC/Karuk - Current), Mid Klamath Coho Rearing Habitat Enhancement (MKWC/Karuk - Current), Fort Goff Culvert Replacement Survey and Design (Caltrans - current), Fort Goff Fish Passage Assessment (Karuk - completed) |  | Re-introduce or encourage beavers. Construct off channel ponds. Screen diversions. Replace Hwy 96 culvert with a bridge. Step pool construction at mouth. Notch swimmer's dams. | Off channel pond, mouth to 0.33 mile |  | Fort Goff culvert replacement (2014, Caltrans) | bar: H to H
Thompson Creek | MK | 123.93 | 199.43 |  | 9 |  | 7 |  | Entrainment?, Lack of LWD in Lower Reach | [14 empty] | A, H, SRd, FR |  |  | Pr, H, Sre, SI, WR | A, H, Sre |  |  | Pr, H, WR, Sre | ? | [5 empty] | Pr, H, All |  | ? | Pr, H, All | Klamath Tributary Fish Passage Improvement (MKWC/Karuk - Current), Mid Klamath Coho Rearing Habitat Enhancement (MKWC/Karuk - Current) |  | Step pool construction annually at mouth. Monitor constructed channel and beaver habitat on Klamath floodplain. Study potential for off-channel habitat construction. | Off channel pond, side channel |  | Thompson Creek Channel Reconfiguration (2009, MKWC/USFS/Karuk/Bella Vista) | bar: H; L to H
[Little] Horse Creek | MK | 118.1 |  |  | na |  | 0.7 | 0.7 | Fish Passage, Channel Structure (Low Pool Volume) | [14 empty] | A, H, SRd, FR |  |  | Pr, H, Sre, SI, WR | A, H, Sre, WR | [9 empty] | Pr, H, All |  |  | A, H, All | Klamath Tributary Fish Passage Improvement (MKWC/Karuk - Current), Mid Klamath Coho Rearing Habitat Enhancement (MKWC/Karuk - Current),Construction of an off-channel pond and addition of LWD (MKWC/USFS/Karuk, secured) |  | Step pool construction at mouth. Add LWD in lower reach. Maintain connectivity to off-channel pool (OCP) at mouth. Add brush bundles to OCP and lower reach. | mouth to 0.1 mile | bar: H; L to H
China Creek | MK | 118.67 | 190.97 |  | na |  | 1 | 1 | Channel/Riparian Structure (Historic Mining Impacts), Fish Passage | H | ?, Review Barrier |  | H | H | H | H |  | H |  | H |  |  | Completed | A, H, SRd, FR | ? |  | Pr, H, Sre, SI, WR | A, H, Sre, WR |  | Pr, H, All | Pr, H, All | [6 empty] | A, H, All |  | Pr, H, Sre, WR | A, H, All | Klamath Tributary Fish Passage Improvement (MKWC/Karuk - Current), Mid Klamath Coho Rearing Habitat Enhancement (MKWC/Karuk - Current), Construction of two off-channel ponds and addition of LWD in lower reach below China Grade Road (MKWC/USFS/Karuk, secured) |  | Step pool construction at mouth. Place LWD in lower reach. Riparian planting. Off-channel/side channel habitat construction. Barrier assessment/removal (if needed, barrier could be natural or related to historic mining). | mouth to slightly above
Cade Creek | MK | 109.84 | 176.77 |  | na |  | 0.5 | 0.5 | Fish Passage, Entrainment | [13 empty] | Pr, H, AM, SRd, FR | A, H, SRd, FR |  |  | Pr, H, Sre, SI, WR |  |  |  |  | Pr, H, Sre, WR | [9 empty] | Klamath Tributary Fish Passage Improvement (MKWC/Karuk - Current), Mid Klamath Coho Rearing Habitat Enhancement (MKWC/Karuk - Current) |  | Replace Hwy 96 culvert with bridge or bottomless arch. Step pool construction at mouth and lower reach. LWD structures in lower 1500' after culvert is replaced. | extensive | bar: H to H
Indian Creek | MK | 106.84 | 171.93 |  | 23.6 |  | 21.6 |  | toxic mine pollution, channelization, urbanization , fish passage, poaching, entrainment in ditches | [13 empty] | Pr, M, AM, SRd, FR | A, H, SRd, FR |  |  | Pr, H, Sre, SI, WR |  | Pr, M, Sre, WR, SI | Pr, H, All | Pr, H, Sre, WR | Pr, ?, Sre |  |  |  | Pr,?,Sre | A,H, All | Pr,H, All | Pr, ?, All | Pr, H, All | A, H, All | Klamath Tributary Fish Passage Improvement (MKWC/Karuk - Current), Baker/Luther Gulch Deisgn Project (MKWC/Karuk, secured) |  | Provide 35% design on a project at Baker/Luther Gulch. Treat ongoing contamination from Grey Eagle Mine. Re-connect or maintain connectivity to exisiting off-channel ponds. Create new off channel ponds, wetlands, and side channels. Add LWD to lower Mill Creek and lower East Fork Indian Creek to impove spawning gravels. Improve water conveyance. Re-locate powerlines away from riparian to reduce chronic impacts to riparian vegetation. | extensive | Large tribs of Indian Creek (SF Indian, EF Indian, Doolittle, West Branch, Mill) need further individual assessment. | bar: H to H
Little Grider Creek | MK | 106.09 | 170.72 |  | na |  | 0.25 |  | Fish Passage | H: H; L: H; H: M; M: ?; M: ?, Dump Above; H: H |  | A, H, SRd, FR |  |  | Pr, H, Sre, SI, WR | A, H, Sre | [7 empty] | ? | ? |  |  |  |  | Klamath Tributary Fish Passage Improvement (MKWC/Karuk - Current), Mid Klamath Coho Rearing Habitat Enhancement (MKWC/Karuk - Current) |  | Step pool construction at mouth. Add LWD to lower reach? | extensive | Hwy 96 crossing may be impacting delta formation. Potential water quality issues from Happy Camp dump drainage.
Elk Creek | MK | 105.9 | 170.42 |  | 11.9 |  | 13.2 | 13.2 | Flood effects from mining/logging in unstable soils, Fish Passage | [13 empty] | Pr, M, AM, SRd, SI | A, H, SRd, FR | Pr, M, AM, SI |  | Pr, M, Sre, SI, WR | A, H, Sre |  |  | Pr, M, Sre, WR | [6 empty] | PR, H, All |  |  | Pr,H, All | Klamath Tributary Fish Passage Improvement (MKWC/Karuk - Current), Mid Klamath Coho Rearing Habitat Enhancement (MKWC/Karuk - Current), Cougar Creek Woodloading Project (MKWC/Karuk, current) |  | Re-introduce or encourage beavers. Construct off channel ponds. Add LWD to East Fork and Cougar Creek to improve gravel storage and coho spawning area. | not known | bar: H to H
Clear Creek | MK | 98.96 | 159.24 |  | 8.9 |  | 8 |  | None | [14 empty] | A, H, SRd, FR | [17 empty] | Klamath Tributary Fish Passage Improvement (MKWC/Karuk - Current), Mid Klamath Coho Rearing Habitat Enhancement (MKWC/Karuk - Current) |  |  | mouth, off channel pond | bar: H to H
Titus Creek | MK | 94.4 |  |  | na |  | 0.5 |  | None | [14 empty] | A, H, SRd, FR |  |  | Pr, H, Sre, SI, WR | A, H, Sre |  |  | Pr, H, WR, Sre | [6 empty] | A, H, WR, Sre |  |  | A, H, All | Klamath Tributary Fish Passage Improvement (MKWC/Karuk - Current), Mid Klamath Coho Rearing Habitat Enhancement (MKWC/Karuk - Current) |  | Concentrate flow into seasonal side channel pools at mouth. Add LWD in lower reach. Create off channel pond above Klamath floodplain. | mouth to 0.9 mile | bar: H; L to H
Independence Creek | MK | 93.88 | 151.08 |  | na |  | 1 |  | None | [14 empty] | A, H, SRd, FR |  |  | Pr, H, Sre, SI, WR | A, H, Sre, WR | [9 empty] | Pr, H, All |  |  |  | Klamath Tributary Fish Passage Improvement (MKWC/Karuk - Current), Mid Klamath Coho Rearing Habitat Enhancement (MKWC/Karuk - Current) |  | Maintain channel flow to upstream braid. Maintain pond connection near mouth. Add cover/complexity and increase edge area of off-channel habitat at mouth. Add LWD in lower reach to improve spawning gravel, pool formation. | mouth | bar: H; L to H
King Creek | MK | 90.9 | 145.78 |  | 0.8 |  | 0.3 |  | Fish Passage | [14 empty] | A, H, SRd, FR |  |  | A, H, Sre, WR | A, H, Sre, WR | [13 empty] | Klamath Tributary Fish Passage Improvement (MKWC/Karuk - Current), Mid Klamath Coho Rearing Habitat Enhancement (MKWC/Karuk - Current) |  | Construct manual LWD structures in lower reach. | MISSING DATA | bar: H; L to H
Ukonom Creek | MK | 89.56 | 144.13 |  | 4.8 |  | 0.1 |  | Fish Passage | [14 empty] | A, H, SRd, FR | [17 empty] | Klamath Tributary Fish Passage Improvement (MKWC/Karuk - Current) |  |  | mouth | bar: H; L to H
Swillup Creek | MK | 88.25 | 142.02 |  | na |  | 0.1 |  | Fish Passage, Lack of LWD | H: H; L: M; H: M; H: ?; M: H |  | A, H, SRd, FR |  |  | Pr, H, Sre, SI, WR | A, H, Sre |  |  | ? | [6 empty] | Pr, H, All |  |  |  | Klamath Tributary Fish Passage Improvement (MKWC/Karuk - Current), Mid Klamath Coho Rearing Habitat Enhancement (MKWC/Karuk - Current) |  | Step pool construction at mouth. Place LWD. Evaluate potential to increase off channel habitat. | extensive
Elliot Creek | MK | 86.94 | 139.9 |  | na |  | 0 |  | Delta Function, Channel Structure, Fish Passage | H: H; L: M; H: M; H: ?; M: H | ? | A, H, SRd, FR |  |  | Pr, H, Sre, SI, WR |  |  | Pr, ?, All | [7 empty] | Pr, H, All |  |  |  | Klamath Tributary Fish Passage Improvement (MKWC/Karuk - Current) |  | Step pool construction at mouth. Place LWD. Evaluate potential to increase off channel habitat. Evaluate effects of Hwy 96 crossing on delta function. | mouth
Aubrey Creek | MK | 86.5 | 139.13 |  | na |  | 0.1 |  | Fish Passage | [14 empty] | A, H, SRd, FR |  |  |  | A, H, Sre | [13 empty] | Klamath Tributary Fish Passage Improvement (MKWC/Karuk - Current), Mid Klamath Coho Rearing Habitat Enhancement (MKWC/Karuk - Current) |  | Manually modify alluvial fan reach to increase thermal refugia capacity. | 0.5 mile | bar: H; L to H
Dillon Creek | MK | 84.12 | 135.37 |  |  |  | 3.1 |  | Fish Passage, Mine Contamination? | H: M; H: H; L: M; M: ?; H: M |  | A, H, SRd, FR | Pr, L, AM, SI | [14 empty] | Pr, H, All |  | Klamath Tributary Fish Passage Improvement (MKWC/Karuk - Current), Mid Klamath Coho Rearing Habitat Enhancement (MKWC/Karuk - Current) |  | Maintain low flow fish passage at mouth. Re-introduce or encourage beaver colonization.
Ti Creek | MK | 79.61 | 126.12 | 6065 | na |  | 1.2 |  | Delta Function, Channel Structure, Fish Passage | [13 empty] | Pr, L, All | A, H, SRd, FR |  |  | Pr, H, SI, Sre, WR | A, H, Sre |  | Pr, M, All | Pr, M, WR, Sre | [6 empty] | A, H, All |  |  |  | Klamath Tributary Fish Passage Improvement (MKWC/Karuk - Current), Mid Klamath Coho Rearing Habitat Enhancement (MKWC/Karuk - Current). Water monitoring wells in place. Cultural Resource Survey by Karuk Tribal staff completed. Proposed restoration project is included within the SRNF Forest-wide Aquatic Restoration Enviromental Analysis. | Instream and Riparian Enhancement Project (MKWC-Karuk-USFS) | The construction of State Highway 96 and the Ti Creek bridge in 1965 confined lower Ti Creek into an incised, single thread channel and disconnected some complex off-channel habitat in this section of the lower-mid Klamath River. This improvement would provide connectivity to off-channel features by excavating this lower river bar to create side-channels, add LWD, enhance remnant wetlands and oxbows to support salmonid habitat. Step pool construction at mouth. Channel stabilization. Research potential to relocate highway out of alluvial floodplain. Restore historic off channel habitat. LWD structures. | mouth to 1.0 mile |  | Fish Passage Imporvement (yearly), Refugia Enhancement i.e. Brush Bundles (Yearly) | bar: H; L to H
Rock Creek | MK | 78.66 | 126.91 | 21312 | na |  | 0.7 |  | Fish Passage | [14 empty] | A, H, SRd, FR | [17 empty] | Klamath Tributary Fish Passage Improvement (MKWC/Karuk - Current), Mid Klamath Coho Rearing Habitat Enhancement (MKWC/Karuk - Current) |  | Bank stabilization in lower reach. Maintain fish passage to section below permanent barrier. | side channel pool, above mouth to 0.3 mile | Important lower reach for fall Chinook and other salmonids. | Fish Passage Imporvement (yearly), Refugia Enhancement i.e. Brush Bundles (Yearly) | bar: H; L to H
Sandy Bar Creek | MK | 76.61 | 123.28 | 3514 | na |  | 0.3 | 0.1 | Fish Passage, Cover Complexity | [14 empty] | A, H, SRd, FR |  |  | Pr, H, SI, Sre, WR | A, H, Sre, WR | ? |  | Pr, H, WR, Sre | [6 empty] | Pr, H, WR, Sre |  | Pr, H, WR, Sre |  | Klamath Tributary Fish Passage Improvement (MKWC/Karuk - Current), Mid Klamath Coho Rearing Habitat Enhancement (MKWC/Karuk - Current) |  | Increase cover complexity of floodplain pools. Create additional off-channel habitat on Klamath floodplain. Step pool construction at mouth. | mouth to 1.0 mile | * Key refugia habitat in this segment of middle Klamath | Fish Passage Imporvement (yearly), Refugia Enhancement i.e. Brush Bundles (Yearly) | bar: H; L to H
Stanshaw Creek | MK | 76.05 | 122.38 | 2664 | na |  | 0.3 | 0.1 | Instream Flows, Fish Passage | [14 empty] | A, H, SRd, FR |  |  | Pr, H, SI, Sre, WR |  | Pr, H, Sre |  | A, H, Sre, WR | A, M, Sre, WR | Pe, H, SRe |  | Pr, M, Sre | Pr, M, Sre |  | Pe, H, All |  | Pr, H, WR, Sre | A, H, All | Klamath Tributary Fish Passage Improvement (MKWC/Karuk - Current), Mid Klamath Coho Rearing Habitat Enhancement (MKWC/Karuk - Current), Stanshaw Creek Instream Habitat Restoration (MKWC - Current). Proposed restoration project is included within the SRNF Forest-wide Aquatic Restoration Enviromental Analysis. | Stanshaw Water Conservation Assessment (MKWC - pending). | Remove sediment plug found at off channel pond at mouth. Step pool construction at mouth to maintain fish passage. Reduce sedimentation from human causes. Add LWD in lower reach. Re-route driveway out of lower reach. Enhance the Klamath River off-channel pool located near mouth to increase summer and winter rearing habitat and juvenile coho survival. Add LWD and boulders in lower reach in order to maintain gradient control, step pool configuration and improve fish passage. This improvement would incorporate bioengineering techniques to improve bank stabilization and vegetative structure and diversity throughout the watershed. Integrate the use of willows, alders, big leaf maple, as well as other native plants to enhance riparian community. Work with all private landowners to improve existing water diversions, reduce water loss and demand, and return flow from MMR diversion to Stanshaw Creek. | mouth to 0.7 mile | * Key refugia habitat in this segment of middle Klamath | bar: H to H
Irving Creek | MK | 75.11 | 120.87 | 5426 | na |  | 1 |  | Fish Passage | [14 empty] | A, H, SRd, FR |  |  | Pr, H, SI, Sre, WR | A, H, Sre | [13 empty] | Klamath Tributary Fish Passage Improvement (MKWC/Karuk - Current), Mid Klamath Coho Rearing Habitat Enhancement (MKWC/Karuk - Current). Proposed restoration project is included within the SRNF Forest-wide Aquatic Restoration Enviromental Analysis. | Instream and Riparian Enhancement Project (USFS SRNF) | This improvement proposes to integrate the use of willows and other native plants to enhance the riparian community and to place logs with rootwads to promote pool scour, cover and diversify existing monotypic habitat features. | mouth, high quality | Address seasonal juvenile and adult fish | bar: H; L to H
Rogers Creek | MK | 72.29 | 116.33 | 4264 | na |  | 0.9 |  | Fish Passage | [14 empty] | A, H, SRd, FR |  |  | Pr, H, SI, Sre, WR | A, H, Sre | [13 empty] | Klamath Tributary Fish Passage Improvement (MKWC/Karuk - Current) | Fish Passage Imporvement Project (in process) | Step pool construction at mouth. | mouth |  | Fish Passage Imporvement (yearly), Refugia Enhancement i.e. Brush Bundles (Yearly) | bar: H to H
Reynolds Creek | MK | 70.04 | 112.71 | 2400 | na |  | 0.1 |  | Fish Passage- Hwy 96 | [36 empty] | Resident steelhead use confirmed. Suspected non-natal coho juvenile rearing in lower 0.25 mi.
Whitmore Creek | MK | 62.34 | 100.32 |  | na |  | 0.1 |  | Fish Passage- Hwy 96, Cover Complexity | [14 empty] | A, H, SRd, FR |  |  |  | A, H, Sre, WR | [13 empty] | Klamath Tributary Fish Passage Improvement (MKWC/Karuk - Current), Mid Klamath Coho Rearing Habitat Enhancement (MKWC/Karuk - Current) |  | Annual step pool construction at mouth, and cover enhancement in off channel pool at mouth. | mouth | bar: H; L to H
Wilson Creek | MK | 61.2 | 99.09 | 1510 | na |  | 0.1 |  | Fish Passage | [14 empty] | A, H, SRd, FR |  |  |  | A, H, Sre | [13 empty] | Klamath Tributary Fish Passage Improvement (MKWC/Karuk - Current), Mid Klamath Coho Rearing Habitat Enhancement (MKWC/Karuk - Current) |  | Step pool construction and brush bundle placement at mouth. | mouth to 0.4 mile | No coho use confirmed in Wilson Creek. | bar: H to H
Pearch Creek | MK | 60.08 | 96.69 | 3910 | na |  | 1 |  | Fish Passage | [14 empty] | A, H, SRd, FR | [19 empty] | Crack bedrock, realign boulders and recreate step pools at mouth to aid passage. |  | No adult or juvenile coho use confirmed in Pearch Creek, only observed holding in refugia near mouth. | bar: H to H
Camp Creek | MK | 57.08 | 91.86 | 27280 | 13.4 |  | 10.8 | 6 | Channelization/Lack of Floodplain Connectivity, Fish Passage, Channel Structure/Lack of LWD | [14 empty] | A, H, SRd, FR |  |  | Pr, H, SI, Sre, WR | A, H, Sre, WR |  |  | A, H, WR, Sre | [6 empty] | A, H, All |  |  |  | Klamath Tributary Coho Habitat Project, Klamath Tributary Fish Passage Improvement (MKWC/Karuk - Current), Mid Klamath Coho Rearing Habitat Enhancement (MKWC/Karuk - Current); Salmonid Habitat Enhancement (USFS-SRNF). Proposed restoration project is included within the SRNF Forest-wide Aquatic Restoration Enviromental Analysis. | Improve spawning/rearing fisheries habitat and accelerate riparian vegetation (USFS-SRNF) | Lower Reach of Camp Creek- Enhance off-channel ponds and braided side-channels. Improve connectivity to channel found on north side of floodplain near mouth. Place LWD with rootwads within backwater stream margins to enhance naturally occurring alcoves and remnant oxbows. Remove proliferation of exotic plants and maintain riparian species composition and structural diversity of native plant community. Accelerate growth of riparian canopy within this entire lower stream reach. Treatments areas may include strategic invasive plant species treatments to improve streamside conditions. Middle/Upper Camp Creek- This improvement would restore complexity and resiliency to instream and off-channel habitats by aligning existing structures, removing old cable and rebar, placing additional LWD, and excavating disconnected side channels. Remove introduced exotic plant species, maintain composition and structural diversity of native plant community and accelerate growth of riparian canopy. | mouth | Important fisheries habitat for fall run Chinook, steelhead, pacific lamprey and other species. Need to better assess coho use in Camp Creek (spawner surveys, winter habitat use). | Fish Passage Imporvement (yearly), Refugia Enhancement i.e. Brush Bundles (Yearly) | bar: H; L to H
Boise Creek | MK | 55.96 | 90.05 | 9987 | na |  | 3.2 | 2 | Fish Passage, Floodplain Connectivity | [14 empty] | A, H, SRd, FR | Pr, M, AM, SRd, FR |  | Pr, H, All | A, H, Sre, WR |  | Pr, H , SI, Sre. WR | Pr, H, WR, Sre | [6 empty] | A, H, All |  |  |  | Klamath Tributary Fish Passage Improvement (MKWC/Karuk - Current), Mid Klamath Coho Rearing Habitat Enhancement (MKWC/Karuk - Current), Instream Habitat Enhancement (SRNF). Proposed restoration project is included within the SRNF Forest-wide Aquatic Restoration Enviromental Analysis. | Boise Creek Coho Habitat Enhancement (MKWC/Karuk/USFS-SRNF) Boise BDA Porject (Set for implementation 2019) | Modify bedrock outcrop and boulders found near the mouth to improve seasonal passage to adult and juvenile fish. Improve and maintain connectivity of existing off-channel beaver ponds. If deemed necessary, consider routing a portion of the creek through beaver ponds and around bedrock cascade near the confluence. Consider potential development of other off channel ponds where cold water seeps connect to the old Klamath River floodplain. Remove invasive plant species found within the area. Enhance the existing riparian plant community to improve root cohesion, roughness and vertical and horizontal vegetative structure. | mouth | Fish passage projects will greatly benefit both coho and chinook salmon. Increasing the size and access to the large beaver pond complex on the Klamath River floodplain upstream of the mouth of Boise Creek would increase non-natal coho use of this high quality habitat. | bar: H to H
Red Cap Creek | MK | 53.33 | 85.81 | 40280 | 19.1 |  | 10.8 | 9 | Off-Channel Habitat, Floodplain Connectivity | H: L; L: M; H: L; H: H; M: M; L: M |  | A, H, SRd, FR |  |  | Pr, H, SI, Sre, WR | A, H, Sre, WR |  | Pr, H , SI, Sre. WR | Pr, M, WR, Sre | [6 empty] | A, H, All |  |  |  | Klamath Tributary Fish Passage Improvement (MKWC/Karuk - Current), Mid Klamath Coho Rearing Habitat Enhancement (MKWC/Karuk - Current); Instream and Riparian Habitat Enhancement (USFS SRNF). Proposed restoration project is included within the SRNF Forest-wide Aquatic Restoration Enviromental Analysis. | Instream and Riparian Enhancement Project (USFS SRNF) Red Cap Design Project LWD (Proposal submitted to Coastal Conservancy 2019) | Lower Reach and Larson's Place- Adjust existing instream structures found within the mainstem and side channel habitat. Add LWD with root wads to increase cover and habitat complexity. Induce favorable hydraulics and connectivity to existing off-channel features. Improve the depth and quality of pool habitat within disconnected side channel features. Remove invasive plant species at strategic locations and plant a diverse array of native riparian species to promote diversity and future LWD recruitment in this stream reach. Middle Reach- (near FS Rd 10N02) This treatment would improve existing fish habitat by removing an old bridge abutment and fence rock gabions. Place additional LWD with root wads in low gradient areas to provide mainstem and side channel habitat. complexity by mimicking natural processes. Stabilize existing side slopes to reduce bank erosion in this stream reach. Upper Reach (near Schnable Diggings) This improvement proposes to adjust existing boulders and place logs with rootwads to provide cover, promote pool scour, sediment sorting and metering, and induce favorable hydraulics and connectivity to existing off-channel features. This treatment includes some streambank restoration to improve stability, promote native species composition, structural diversity and integrity of existing riparian plant community. Re-introduce or encourage beavers. | mouth | Important fisheries habitat for fall run Chinook, steelhead, pacific lamprey and other species. Continue to evaluate and address large wood accumulation and steelhead passage on the upper mainstem at RM 10.8.
Slate Creek | MK | 51.07 | 82.19 | 8747 | na |  | 4.7 | 2.5 | Fish Passage | [14 empty] | A, H, SRd, FR |  |  | Pr, M, SI, Sre, WR | A, H, Sre, WR | [13 empty] | Klamath Tributary Fish Passage Improvement (MKWC/Karuk - Current), Mid Klamath Coho Rearing Habitat Enhancement (MKWC/Karuk - Current); Instream Habitat Enhancement (USFS SRNF). Proposed restoration project is included within the SRNF Forest-wide Aquatic Restoration Enviromental Analysis. | Riparian Enhancement Project (USFS SRNF) | Continue to assess possible step pool construction at mouth and concentrate flow by moving rocks with hand crews to maintain connectivity. Other treatments would incorporate bioengineering techniques to improve bank stabilization and vegetative structure and diversity in the lower reaches. Enhance riparian vegetation/structure to aid with recruitment and instream cover. In-stream LWD structures would be added to promote channel scour and thalweg development, as well as increase spawning and rearing fisheries habitat. Consider possible re-introduction of beavers. | mouth | Has small population of spawning coho. Late fall run fish frequently spawn until February in the trib. | bar: H; L to H
Bluff Creek | MK | 50.32 | 80.98 | 47440 | 40 |  | 8.4 | 5 | Fish Passage, Winter Rearing Habitat | [21 empty] | Pr, H, WR, Sre | [10 empty] | Klamath Tributary Fish Passage Improvement (MKWC/Karuk - Current); Instream Habitat Enhancement (Ongoing USFS SRNF). Proposed restoration project is included within the SRNF Forest-wide Aquatic Restoration Enviromental Analysis. | Bluff Creek Instream and Off Channel Habitat Enhancement (USFS SRNF) | Enhance existing instream and off channel habitat (USFS-SRNF and others). Wright's Ranch- Since the mid-1980's, fisheries enhancement projects have occurred in Bluff Creek. This treatment would improve existing fish habitat by align existing boulders to improve off-channel connectively and habitat diversity, placing additional LWD to increase cover, detritus retention and side channel complexity, and stabilize existing lower hillslopes to reduce bank erosion in this reach. Dragon Bar- This improvement proposes to adjust and improve existing boulders and place logs with rootwads to provide cover, promote pool scour, sediment sorting and metering, and induce favorable hydraulics and connectivity to existing off-channel features. Upper Bluff (near FS Rd 12N13H)- This upper steelhead habitat is lacking instream habitat complexity. The placement of LWD in this low gradient reach would create pools, provide cover, reduce gravel movement and enhance slow water fish habitat. | none | Need to assess further assess coho rearing habitat thoughout the lower-middle reaches of Bluff Creek. In addition, continue to evaluate and address steelhead passage concerns at the large wood accumulation found on the lower East Fork. It is important to also note that access is closed during the Wet Weather Season (mid Oct to late May) due to concerns over the spread of Port Orford Cedar Root Disease. | bar: H to H
Aikens Creek | MK | 49.57 | 79.77 | 2526 | 0.6 |  | 0.6 | 0.6 | Winter Rearing Habitat, Floodplain Connectivity, Riparian Enhancement | [14 empty] | A, H, SRd, FR |  |  | A, H, SI, Sre, WR | A, H, Sre, WR |  | Pr, H , SI, Sre. WR | Pr, H, WR, Sre | [10 empty] | Klamath Tributary Fish Passage Improvement (MKWC/Karuk - Current), Mid Klamath Coho Rearing Habitat Enhancement (MKWC/Karuk - Current); Instream Habitat Enhancement (USFS SRNF). MKWC monitoring wells installed, Karuk Tribe Cultural Resource Survey completed. Proposed restoration project is included within the SRNF Forest-wide Aquatic Restoration Enviromental Analysis. | Aikens Creek Channel Reconfiguration and Floodplain Reconnectivity (Karuk/MKWC/USFS); Riparian Enhancement Project (USFS-SRNF and others). | The lower mile of Aikens Creek occupies the pre-1964 Bluff Creek channel. Currently, the existing stream channel is simplified due to the changes resulting from previous floods, the placement of the existing road and associated dispersed campsites. This treatment would widen the channel and reconnect a portion of the remnant floodplain by removing accumulated bedload deposits. Create and restore off-channel ponds, side-channels, and wetland. Side channel ponds will be created to restore complexity for instream and off-channel salmonid habitat. Placement of LWD will enhance spawning and overwintering rearing fish habitat. Removal of invasive non-native plants will improve the health of existing native vegetation. Riparian plantings will increase shade, enhance vertical/horizontal structure and diversity, and promote future LWD recruitment to the site. (MKWC, USFS-SRNF, Cal Trans, CDF&W, AmeriCorps, Orleans Elementary, Karuk & Yurok Tribes and others). | none | Key refugia in this segment of lower-mid Klamath. Fall Chinook spawning and rearing, Karuk snail occupancy | bar: H; L to H
Hopkins Creek | MK | 47.32 | 76.15 | 5769 | na |  | 1 |  | Fish Passage | [14 empty] | A, H, SRd, FR |  |  |  | Pr, H, Sre, WR |  | Pr,H ,Sre. WR | [11 empty] | Klamath Tributary Fish Passage Improvement (MKWC/Karuk - Current), Mid Klamath Coho Rearing Habitat Enhancement (MKWC/Karuk - Current) | Modify existing channel structure at mouth and improve riparian habitat to aid with recruitment (USFS-SRNF and others). | Crack bedrock/boulders at mouth to create step pools that will aid with fish passage. Girdle small diameter riparian vegetation within lower mile to increase light, productivity and jump start stand development (USFS-SRNF and others). |  | Need to assess coho spawning and winter rearing in Hopkins Creek, as well as the potential for developing winter rearing habitat. | bar: H to H